## Tabelle1
|  |  | example | Month 2 | Month 6 | Month 10 | Month 14 | Month 18
A | Target price | (See “Contract”) | 48675000
B | PROJECTED TOTAL COSTS | (See “Resourcing”) | 51387500
C | Total cost undershoot overshoot adjustment | If “Fixed Price”: ZERO
|  | If “50/50 Pain Gain Share”: (B - A) x 50% | 1356250 | 0 | 0 | 0 | 0 | 0
D | Client overhead | 50,000 per month x duration of project (See “Bar Chart”) | 1300000
E | Liquidated damages reduction in price | 500,000 per month for any delays not due to extra scope (See “Bar Chart” & “Scope Options”) | 500000
F | TOTAL PRICE (PROJECTED) | A + C + D - E | 50831250 | 0 | 0 | 0 | 0 | 0
Update the "Estimated Total Price" number (to the nearest million) on the "Outcomes" App